**Pupil Premium Plan - 2019/20**

|  |  |
| --- | --- |
| **Review** | **July 2020** |
| **Pupil Premium Grant** | **£19,767** |
| **Additional funding** | **£6,800** |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Objective** | **Rationale and actions** | **Measured impact** | **Time scales** | **Lead by** | **Cost / resources** | **Success criteria** |
| Improve reading progress so PPG children achieve at or above expected levels | Reading assessments;Reading schemes to support accelerated progress for EYFS and KS1Phonics support;Reading programme to offer additional practice;Expert reading support programme as an intervention; | Tracking of PPG data by SLT (termly data, baseline data and teacher assessment.PP meetings termlyTracked results of intervention through provision meetings and 2PPs | Review in Spring, after round of interventions and assessments. | SLTSENCoEnglish Lead | Assessment tests - £500Reading schemes - £2000Phonics additional resources from HFL - £500Grandparent helpers - time for training and review - £600 Teacher time for assessing and delivering interventions - £6000Time for intervention review - £1000**Total - £10,600** | Improved progress scores in assessments for individuals - PM BenchmarkBert’s reading test (reading age) |
| Improve maths progress so that PPG children achieve in line with non PPG peers  | Maths assessments for all children Yr 1 and aboveAdditional assessments for vulnerable learnersMaths advisor timeMaths improvement projectEvidence-based interventions e.g. Jigsaw maths and Plus programme | Tracking of PPG data by SLT (termly data, baseline data and teacher assessment.PP meetings termlyTracked results of intervention through provision meetings and 2PPsInternal moderationBook scrutinies Reviews data submitted to improvement project | Termly review of data and yearly project review alongside whole school data. | SLT and maths LeadMaths advisor and HCC team | Cost of participation in project and advisor time - £1500Teacher time for assessments - £2000Resources and training for interventions - £1000**Total - £4500** | Improved progress scoresCoherent and consistent planning evidenced in booksImproved reasoning evidenced in books and through diagnostic assessments |
| Enable opportunities for enrichment for PPG children.  | Programme of added curricular/arts experiences History off the PageAuthor visitsWeekly music lessonsDiscosSchool trips e.g. PGL |  | Yearly review of take up | SLTSubject leads | **Total - £3,267** | All children able to access activities |
| Improve ICT to enable children to be supported immediately and for future benefit. | Invest in Clicker 7Purchase laptops dedicated for specific identified childrenPurchase teacher ipads and apps and trial these in class with teachersProvide interventions to enable children to develop more proficient touch typing |  | Termly feedback on added benefit from staff.Learning walksMonitoring the dance mat programme resultsIncreased use of ICT for work produced by vulnerable learners. | SLTICT Lead | Clicker - £2300Laptops and ipads - £4500Intervention time - £1400**Total - £1400** | Enable all children who have disadvantage to be able to confidently and expertly use technology to close the gaps in learning experience and to overcome barriers to learning. |